**Coordination Call SFU dustfall**

**Additions highlighted in yellow**

**Present: Pete Golden, Bamdad Hosseini, John Stockie**

Toll-Free:                             1-866-546-3377

Toll:                                        1-719-234-7872

Host Passcode:                 2527601

Participant Passcode:     252760

|  |  |  |
| --- | --- | --- |
| **Item** | **Status** | **Responsibility /Due Date** |
| Additional data | TSP’s, existing dustfall locations and Xact data may be useful, provide to SFU.   * Duncan only during the duration of study, * Butler Park analyzer down, provide last summer’s data and wind. | Discuss timeline for Xact data (we have 3 years in one location, 2 months in the other) |
| Dustfall Deployment | Majority of deployment on Aug 20. Collect samples Thurs 19th and Friday 20th. Note time and date of collection.   * May identify another period of deployment based on long-term forcast. | NA |
| Data | Location of dustfalls – Forward to SFU team – GPS Locations | ASAP |
| Data | Location of existing sources   * Forward to SFU team * Include time of emissions estimates if time-sensitive * Signatures of materials – if there is a signature of material that is emitted in defined locations, this info is usefull. * Roads map and fugitive emissions work – Bill Jankola | Require assumed emissions coordinates (PGG) |
| Data | Expect early Oct for assays of dustfalls based on collection end of September. | Oct |
| Data | Assay will include Zn – Will investigate Sulphate etc. | PGG - Oct |
| MITACS | Purchase requisition has been entered, awaiting PO. | ASAP |
| Timeline | Target site visit for first week of October   * Afternoon on 1’st, morning 2nd. * Will look into fugitive reduction project orientation. * Include tour of the smelter. * PGG to arrange PPE. | Oct |
| Timeline | Target Feb 2014 for final results. There is some risk to this based on behavior of the model and quality of data. | Feb |

**Peter Golden P.Eng.**

Environmental Specialist

**Teck** | Trail Operations

**Phone +** 1 250 364 4315

[Peter.Golden@teck.com](mailto:peter.golden@teck.com)